Membership Growth Event Checklist

Six weeks prior

Evaluate your club by utilizing following tools:

- Membership Satisfaction Guide

- Blueprint for a Stronger Club

- Club Quality Initiative (CQI)

- Your Club, Your Way!

Conduct community needs assessment

- Appoint committee.

- Evaluate current projects.

- Identify target audience and community service needs.

- Consider new projects.

Conduct community needs assessment

- Identify membership committee organizers. 
[ party planners (logistics/setup) | marketing | database | budget ]

- Set up membership growth goal (at least 5% growth).

- Set date/time/place for membership event.

- Communicate date to zone chair, district governor and 
GMT district coordinator.

- Develop budget for event.

- Determine theme of event or dinner.

Five weeks prior

Request and order from Lions Clubs International 
and the Lions International Shop

- Membership applications and brochures (or print from website)

- Lions International decorations

Key event items

- Identify and invite speakers from community partner or service benefactors.

- Identify and invite guest speaker.

- Identify master of ceremony.

- Identify a Lion who will input prospective member information into database.

- If food will be served, develop the menu.

- Secure equipment needs: audio/video (speakers, microphone, projector and screen).

- Secure other supplies: table covers, name tags, paper, envelops, club letterhead.

Four weeks prior

Club meeting and presentation

- Promote the membership growth event to club members

- Distribute recruiting wheel and Build a Lions Network 
(pages 16-17, ME-300).

- Ask each member to nominate seven prospective members and submit names to database manager.

- Identify volunteers for set up and clean up the day of the event.

Three weeks prior

Review

- Collect the “Build a Lions Network Form” from members. 
(Goal is to have 100% participation.)

- Review and preapprove all nominees.

- Print invitation letter, ensure each letter is personally signed by president and mail to prospective members.

- Confirm all items requested by Lions International and the Lions International Shop have been received.

- Confirm the status of all guests and speakers

Two weeks prior

Data and script

- Distribute follow-up data and script to all club members.

One week prior

Sponsors and committee

- Sponsor follows up with prospective members to confirm attendance and notifies database manager.

- Database manager reports attendance numbers to food committee.

- Report status of each nominee to database manager.

- Report all new members in MyLCI.

Day of event

Set up

- Decorate room.

- Check audio and video equipment.

- Set up “Sign-in Table,” name tags and membership applications.

- Set up food and refreshments.

- Follow proposed agenda.

After the event

- Distribute follow-up data and script to all club members.

Within 72 hours after the event

- Contact nominees who attended but did not join.

- Contact nominees who confirmed but did not attend.

- Report status of each nominee to database committee or manager.

No later than the 25th of the month

- Report all new members in MyLCI.